## Timeline
|  | Start |  |  | End
DRAFT NSSP Implementation Plan Timeline DRAFT | 2015 | [13 empty] | 2016
| July |  |  | August |  |  | September |  | October |  |  | November |  | December | January | February | March | April |  | May |  | June |  | July |  |  |  | August |  |  | September |  |  | October |  |  | November |  | December
Develop Master Facility Table Plan | 1 |  |  | 1
Install /Assess foundational SAS tools and start use for data quality activities at DHIS | 1 | [19 empty] | 30
Resolve Key Issues Identified during Pilot that are mandatory for ESSENCE Implementation | 1 | [9 empty] | 30
Duplicate Existing Databases to MS SQL on separate server |  |  | 15 |  |  |  | 1
Stand-up ESSENCE Staging Environment |  |  |  | 1 | [6 empty] | 30
Develop ESSENCE Data Flows | [5 empty] | 15 | [6 empty] | 30
Add variables to ESSENCE Databases (PHIN Messaging Guide v2.0 Table 4.2) | [5 empty] | 15 | [6 empty] | 30
Implement Master Facility Table Plan with all Jurisdictions | [5 empty] | 20 | [14 empty] | 30
Develop ESSENCE Administration Tool for Alpha/Beta Testing (Staging) | [6 empty] | 1 | [6 empty] | 1
Develop Technial Assistance Documentation | [6 empty] | 1 | [13 empty] | 30
Purchase R Studio Server Pro | [7 empty] | 15
Scan Data Mart Server | [7 empty] | 15 |  | 10
Research Approaches for a Single Sign-on Solution | [7 empty] | 15 | [12 empty] | 30
Test ESSENCE Administration Tool for Alpha/Beta Jurisdictions (Staging) | [11 empty] | 1 | [6 empty] | 30
Transition Jurisdictional Pilots to Staging Environment: Tennessee / Wisconsin / Adams, CO / Arapahoe, CO / Douglas, CO / Virginia / Marion County, IN / Seattle-King County, WA / Michigan / VA / DoD | [13 empty] | 1 |  |  |  |  | 30
Adjust ESSENCE Settings | [13 empty] | 1 |  |  |  |  | 30
Move Staging Environment settings to Production Environment | [17 empty] | 1 | 30
Scan ESSENCE Environment | [17 empty] | 1 |  |  | 30
Assess Exposing SAS Web Studio and R Studio Server Pro to Jurisdictions | [21 empty] | 1 | [18 empty] | 30
Transition to ESSENCE: Illinois (includes Cook) / Massachussets / Kentucky / Arizona / Mississippi / Arkansas / West Virginia / Kansas / Houston, TX | [21 empty] | 1 |  |  | 10
Transition to ESSENCE: Nevada / Utah / New Mexico / Denver Public Health / Riverside, CA / Idaho** / North Dakota / Montana /Alaska | [22 empty] | 20 |  |  |  | 30
Transition to ESSENCE: Stanislaus, CA / Linn County, IA / Santa Clara, CA / Nevada, CA / Florida / Ohio /Pennsylvania / New York / North Carolina | [25 empty] | 20 |  |  |  | 30
Transition to ESSENCE: Georgia / New York City / New Jersey / Indiana / Tarrant County TX / Missouri / Louisiana Maryland / Washington | [28 empty] | 20 |  |  |  | 30
Facility Administration Tool Development | [27 empty] | 1 | [12 empty] | 30
Transition to ESSENCE: Oklahoma / Minnesota / Connecticut / South Carolina / Oregon / Maine / Nebraska / New Hampshire / Rhode Island | [31 empty] | 20 |  |  |  | 30
Transition to ESSENCE: Boston Public Health Commission / County of Sacremento, CA*** / District of Columbia Delaware / San Diego, CA / Hawaii / Vermont / South Dakota / San Mateo, CA | [34 empty] | 20 |  |  | 30
Sunset BioSense Web Application | [39 empty] | 16 | 30
PHASE I
PHASE II
PHASE III
PHASE IV